## Functional Automation Estimate
Automating Manual Tests
Number of Test Cases | 205 | [5 empty] | Project Name | Issuetrak
[7 empty] | Z - Total Test Cases | 205 | Quantity
Time Per Script for Automation | 4.8 | Hours per Script |  |  |  |  | Average # of Steps in TC | 11 | Quantity
Total time for Automation, Hours | 984 | Total Hours, all Scripts |  |  |  |  | Content & Thoroughness of Steps in TC | 90% | Subjective
Hours per day | 8 | Hours per Day |  |  |  |  | # of Applications/Systems | 1 | Quantity
Total time for Automation, Days | 123 | Total Days, all Scripts |  |  |  |  | Complexity based on Content & Thoroughness Low is >85% Med is 60-85% High <60% If test cases are very detailed, then Complexity is Low If test cases require some followup with project team, then Complexity is Med If test cases require significant input from project team, then Complexity is High | Med | Calculation
Team Members Automation Testing | 1.25 | Team Members |  |  |  |  | A - Total Components Needed based on Complexity (12 - Low, 18 - Med, 24 - High) | 12 | Configuration
Duration, Automation Testing, Days | 98.4 | Total Duration, in Days |  |  |  |  | B - Total Hours Needed Per Component based on Complexity (10 - Low, 20 - Med, 30 - High) | 10 | Configuration
Estimated Start Date | [6 empty] | C - Script Defect Triage/Resolution/Re-test based on # of TC or # of Steps If test cases or steps 25-50, then 40 If test cases or steps 50-75, then 100 If test cases or steps 75-100, then 150 | 40
Estimated End Date | [6 empty] | D - Additional Hours based on # of Systems If # of systems is 1, then 0 If # of systems is 2, then 100 If # of systems is >2, then 200 | 0
PreAnalysis Hours | [6 empty] | E - Additional Hours based on # of Environments If # of environments is 1, then 40 If # of environments is 2, then 80 If # of environments is 3 or Prod, then 120 | 40
| Estimate | [5 empty] | F - Total Hours Needed (A x B) + C + D + E | 200 | Calculation
| Duration, in Days | [5 empty] | Total Hours Needed Per TC (F/Z) | 0.97561 | Calculation
Team Member | Days | Particip. | Hours / Day | Total Hrs | $ / Hr | Total / Team Mbr
Onshore Lead | 98.4 | 25% | 8 | 197 | 75 | 14775
Offshore | 98.4 | 100% | 8 | 787 | 25 | 19675
|  |  |  | 984 |  | 34450